## Overall
Work Breakdown Structure |  |  |  | Sport Booking
Project Start |  | 2024-09-08 |  | 8h/point
No | Story ID | Story | Priority | Storypoint
1 | ST000 | Project Initiation | HIGHT | 8
2 | ST001 | Initialize backend project (bsa) | HIGHT | 1
3 | ST002 | Config develop environments | HIGHT | 0.5
4 | ST003 | Design architecture and APIs | HIGHT | 1
5 | ST004 | Create utilities module | HIGHT | 1
6 | ST005 | Implement APIs | HIGHT | 5
7 | ST006 | Implement unittest / Testing | MEDIUM | 3
8 | ST007 | Initialize User mobile application (uma) | HIGHT | 1
9 | ST008 | Implement Login/Register screens (5 screens) | HIGHT | 3
10 | ST009 | Implement Home screens | HIGHT | 1
11 | ST010 | Implement Explore screens (3 screens) | HIGHT | 3
12 | ST011 | Implement Booking screens (7 screens) | HIGHT | 3
13 | ST012 | Implement Details and Profile screens (3 screens) | HIGHT | 2
14 | ST013 | Implement unittest / Testing | MEDIUM | 3
15 | ST014 | Initialize Owner mobile application (oma) | MEDIUM | 1
16 | ST015 | Implement Login/Register screens (5 screens) | MEDIUM | 2
17 | ST016 | Implement Home screens | MEDIUM | 2
18 | ST017 | Implement Club screens | MEDIUM | 1.5
19 | ST018 | Implement Notify screens | MEDIUM | 0.5
20 | ST019 | Implement User screens | MEDIUM | 1
21 | ST020 | Implement Profile screens | MEDIUM | 2
22 | ST021 | Implement Analyze screens | MEDIUM | 2
23 | ST022 | Implement unittest / Testing | MEDIUM | 2
24 | ST023 | Initialize Owner web application (owa) | MEDIUM | 1
25 | ST024 | Implement Login/Register screens (3 screens) | MEDIUM | 2
26 | ST025 | Implement Home screens | MEDIUM | 1
27 | ST026 | Implement Club screens | MEDIUM | 1
28 | ST027 | Implement Notify screens | MEDIUM | 0.5
29 | ST028 | Implement Profile screens | MEDIUM | 2
30 | ST029 | Implement Analyze screens | MEDIUM | 2
31 | ST030 | Implement User screens | MEDIUM | 1
32 | ST031 | Implement unittest / Testing | MEDIUM | 2
33 | ST032 | Initialize Admin web application (awa) | MEDIUM | 1
34 | ST033 | Implement Login/Register screens (3 screens) | MEDIUM | 2
35 | ST034 | Implement Home screens | MEDIUM | 2
36 | ST035 | Implement Club screens | MEDIUM | 1
37 | ST036 | Implement User screens | MEDIUM | 1
38 | ST037 | Implement Analyze screens | MEDIUM | 2
39 | ST038 | Implement Notify screens | MEDIUM | 1
40 | ST039 | Implement Profile screens | MEDIUM | 2
41 | ST040 | Implement unittest / Testing | MEDIUM | 3
42 | ST041 | Deploy to production | LOW | 2
TOTAL |  |  |  | 79

## WBS
PROJECT TITLE | Sport Booking
PROJECT MANAGER | LoanTT
COMPANY NAME
DATE | 2024-09-08
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
[6 empty] | COMPLETE | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Project Initiation
1.1 | Requirement analyze | LoanTT | 2024-09-08 | 2024-09-08 | 1 | 100%
1.2 | Create WBS and estimate | LoanTT | 2024-12-08 | 13/08/2024 | 2 | 100%
1.3 | Design mockup | LoanTT | 2024-09-08 | 2024-11-08 | 3 | 100%
1.4 | Design database | LoanTT | 2024-11-08 | 2024-12-08 | 2 | 100%
2 | Initialize backend project (bsa)
2.1 | Create project and define source code structure | LoanTT | 13/08/2024 | 13/08/2024 | 1 | 100%
3 | Config develop environments
3.1 | Config develop environments | LoanTT | 13/08/2024 | 13/08/2024 | 0.5 | 100%
4 | Design architecture and APIs
4.1 | Design architecture | LoanTT | 14/08/2024 | 14/08/2024 | 0.5 | 0%
4.2 | Design APIs | LoanTT | 14/08/2024 | 14/08/2024 | 0.5 | 0%
5 | Create utilities module
5.1 | Create common module (logger, middleware, …) | LoanTT | 15/08/2024 | 15/08/2024 | 1 | 0%
6 | Implement APIs
6.1 | Implement APIs – auth | LoanTT |  |  |  | 0%
6.2 | Implement APIs – unit | LoanTT |  |  |  | 0%
6.3 | Implement APIs – location | LoanTT |  |  |  | 0%
6.4 | Implement APIs – metadata | LoanTT |  |  |  | 0%
6.5 | Implement APIs – booking | LoanTT |  |  |  | 0%
6.6 | Implement APIs – media | LoanTT |  |  |  | 0%
6.7 | Implement APIs – club | LoanTT |  |  |  | 0%
6.8 | Implement APIs – analyze | LoanTT |  |  |  | 0%
6.9 | Implement APIs – user | LoanTT |  |  |  | 0%
7 | Implement unittest / Testing
7.1 | Implement unittest | LoanTT |  |  |  | 0%
8 | Implement Login/Register screens (5 screens)
8.1 | Implement login screens and controller | LoanTT |  |  |  | 0%
8.2 | Implement register screens and controller | LoanTT |  |  |  | 0%
8.3 | Implement start screens and controller | LoanTT |  |  |  | 0%
8.4 | Implement change password screens and controller | LoanTT |  |  |  | 0%
8.5 | Implement reset password screens and controller | LoanTT |  |  |  | 0%
9 | Implement Home screens
9.1 | Implement Home screens and controller | LoanTT |  |  |  | 0%
9 | Implement Club screens